## Sayfa1
RBS ID | Category | Description | Probability | Impact | Mitigation | Contingency | Risk Score after Mitigation | Risk Owner | Risk Status
R1 | Security | Inadequate handling of sensitive patient data during development or testing | Low | High | Use anonymized or synthetic datasets; apply data encryption where applicable | Remove identifiable data and re-run pipeline with dummy inputs | Low | Team | Active
R2 | Validation | Difficulty in validating data accuracy and interoperability due to lack of real hospital data | Medium | High | Use open-source NICU datasets and synthetic data generators | Collaborate with mentors or use publicly available test case | Low | Team | Active
R3 | Team Skill Gap | Team may lack deep expertise in healthcare data standards like HL7/DICOM | Medium | Medium | Assign learning tasks and short tutorials early in project | Focus on simplified FHIR implementation only | Medium | Team | Active
R4 | Communication | Lack of communication between the parties involved in the project will impact the progress negatively | Medium | High | Establish clear communication plans, use collaborative tools for easier backlog tracking, set up frequent meetings. | Escalate the issue to the project supervisor or advisor. Conduct a focused team session to address and resolve specific communication barriers. | Low | Team | Active
R5 | Testing | Testing the project directly on a NICU might not be possible whenever testing is needed. | High | Medium | Use recorded or anonymized NICU data to test without needing input from a working unit. | Document the testing limitations clearly in the final report. | Medium | Team | Active